## List with Pending or Done
|  | App | Web
Changes I would like in project | Grouping of importance | Change in project Status | Change in project Status
Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. |  | Done | Done
When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Done | Done
Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. |  | Done | Done
In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Done | Done
Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). |  | Done | Done
Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. |  | Done | Done
If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" |  | Done | Done
"Key Accepted" should show on either project only if key is valid showing invalid if it isnt |  | Done | Done
Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Done | Done
I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Done | Done
Most recent working zip version uploaded () use it as a base to these changes. Add: |  | Done | Done
1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. |  | Done | Done
2.) Remove old Logout button |  | Done | Done
Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. |  | Done | Done
Setting to set to speak on both term and pronunciation |  | Done | Done
5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Done | Done
6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Done | Done
a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) |  | Done | Done
b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. |  | Done | Done
c.) Add option to Change between Study subject flashcards via json files (manually or AI created) |  | Done | Done
Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it |  | Done | Done
Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. |  | Done | Done
In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. |  | Done | Done
Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} |  | Done | Done
In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. |  | Done | Done
Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. |  | Done | Done
Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. |  | Done | Done
In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. |  | Done | Done
1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) |  | Done | Done
Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. |  | Done | Done
4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text |  | Done | Done
In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. |  | Done | Done
If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. |  | Done | Done
Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. |  | Done | Done
If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. |  | Done | Done
Saved breakdown text below "Select group..." dropdown does not change on changing cards |  | Done | Done
As admin>Stats: to see who is actively/recently logged in and studying |  | Done | Done
Notes to be added to cards, to view if selected. Option to share and collaberate with others. |  | Done | Done
Next thing is to add png image and to change the color a little to match the company colors |  | Done | Done
Run as service |  | Done | Done
and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app. |  | Done | Done
App needs to have a way to change its url pushed from webserver or pushed from app admin to other users. I don’t want other users seeing my url in app.
WebserverPackage (wsp) Windows still thinks the version installed is v1.0.0 that needs to be updated as it changes versions, An option in tray settings to auto start with system and open gui on start.
Have custom deck also sync with other devices
Sort "all" cards deck by status dropdown,
Webserver (ws) make reshuffle button same size as random toggle, I don’t like how everything below it moves down, only random toggle on custom page does not stay toggled.
in ws User guide page is basic and download user guide isnt working goes to a white page with "Internal Server Error The server encountered an internal error and was unable to complete your request. Either the server is overloaded or there is an error in the application."
in ws In admin "quick action" highlight is stuck on "Check Health", each tab need to be highlighted when veiwing that tab. Can we make quick actions text look less cms promptish. Remove Card Groups section in Admin. Replace with something cool.
in ws when clicked total users see users info, to give admin or to force password change, resetting to default 123456789 and require set new password.
The cards are there, not sure why it shows missing, the AI works on breakdowns, but the button does not work, and the Ai generated new card definitions has that error. When I manually add the fields, the add card button didn't do anything. | #VALUE! | #VALUE!

## Android app updates Status
Changes I would like in project | Grouping of importance | Change in project Status | Pending or Done | Evidence (file hits) | Confidence
Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. |  | Not verified in current zip | Pending |  | Low
When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Verified in current zip (match: created by sidney shelton) | Done | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | High
Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. |  | Verified in current zip (match: web app sync) | Done | KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | High
In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Verified in current zip (match: created by sidney shelton) | Done | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | High
Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). |  | Verified in current zip (match: sync breakdowns, web app sync) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt | High
Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. |  | Verified in current zip (match: chatgpt api, gemini api, web app sync) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt | High
If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" |  | Not verified in current zip | Pending |  | Low
"Key Accepted" should show on either project only if key is valid showing invalid if it isnt |  | Verified in current zip (match: key accepted) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | High
Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Verified in current zip (match: ai access settings, key accepted, key invalid) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt | High
I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Verified in current zip (match: sync breakdowns, auto select, chatgpt) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt | High
Most recent working zip version uploaded () use it as a base to these changes. Add: |  | Not verified in current zip | Pending |  | Low
1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. |  | Not verified in current zip | Done |  | Low
2.) Remove old Logout button |  | Not verified in current zip | Pending |  | Low
Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. |  | Verified in current zip (match: unlearned, unsure, learned) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
Setting to set to speak on both term and pronunciation |  | Not verified in current zip | Pending |  | Low
5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Verified in current zip (match: custom, unsure, learned) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Verified in current zip (match: custom, unsure, learned) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) |  | Not verified in current zip | Pending |  | Low
b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. |  | Not verified in current zip | Done |  | Low
c.) Add option to Change between Study subject flashcards via json files (manually or AI created) |  | Not verified in current zip | Pending |  | Low
Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it |  | Not verified in current zip | Pending |  | Low
Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. |  | Verified in current zip (match: unsure) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. |  | Verified in current zip (match: custom, unsure, got it) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} |  | Verified in current zip (match: custom, random order, show group label) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | High
In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. |  | Verified in current zip (match: unsure, got it) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. |  | Not verified in current zip | Pending |  | Low
Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. |  | Verified in current zip (match: learned, study, custom) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. |  | Not verified in current zip | Pending |  | Low
1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) |  | Verified in current zip (match: active, unsure) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. |  | Verified in current zip (match: active, reset to default settings, to learn) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text |  | Verified in current zip (match: learned) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | High
In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. |  | Verified in current zip (match: buttons) | Done | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | High
If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. |  | Not verified in current zip | Done |  | Low
Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. |  | Not verified in current zip | Done |  | Low
If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. |  | Not verified in current zip | Pending |  | Low
Saved breakdown text below "Select group..." dropdown does not change on changing cards |  | Not verified in current zip | Pending |  | Low
As admin>Stats: to see who is actively/recently logged in and studying |  | Not verified in current zip | Pending |  | Low
Notes to be added to cards, to view if selected. Option to share and collaberate with others. |  | Not verified in current zip | Pending |  | Low
Next thing is to add png image and to change the color a little to match the company colors |  | Not verified in current zip | Pending |  | Low
Run as service |  | Not verified in current zip | Pending |  | Low
and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app. |  | Not verified in current zip | Pending |  | Low

## Web Server updates Status
Changes I would like in project | Grouping of importance | Change in project Status | Pending or Done | Evidence (file hits) | Confidence
Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. |  | Not verified in current zip | Pending |  | Low
When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Verified in current zip (match: created by sidney shelton) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/static/user-guide.html | High
Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. |  | Not verified in current zip | Pending |  | Low
In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Verified in current zip (match: created by sidney shelton) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/static/user-guide.html | High
Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). |  | Not verified in current zip | Done |  | Low
Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. |  | Verified in current zip (match: gemini api) | Done | KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/admin.html | High
If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" |  | Not verified in current zip | Pending |  | Low
"Key Accepted" should show on either project only if key is valid showing invalid if it isnt |  | Not verified in current zip | Pending |  | Low
Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Verified in current zip (match: chatgpt, gemini, ai access settings) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/admin.html | High
I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Verified in current zip (match: chatgpt, gemini) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/admin.html | High
Most recent working zip version uploaded () use it as a base to these changes. Add: |  | Not verified in current zip | Pending |  | Low
1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. |  | Not verified in current zip | Done |  | Low
2.) Remove old Logout button |  | Not verified in current zip | Pending |  | Low
Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. |  | Verified in current zip (match: unlearned, unsure, study) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/BRANDING_NOTE.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json | High
Setting to set to speak on both term and pronunciation |  | Not verified in current zip | Pending |  | Low
5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Verified in current zip (match: custom, unsure, unlearned) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json | High
6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Verified in current zip (match: custom, unsure, random order) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json | High
a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) |  | Not verified in current zip | Pending |  | Low
b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. |  | Not verified in current zip | Done |  | Low
c.) Add option to Change between Study subject flashcards via json files (manually or AI created) |  | Not verified in current zip | Pending |  | Low
Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it |  | Not verified in current zip | Pending |  | Low
Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. |  | Verified in current zip (match: unsure) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. |  | Verified in current zip (match: custom, unsure, relearn) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} |  | Verified in current zip (match: custom, random order, reverse the cards) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html | High
In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. |  | Verified in current zip (match: unsure, got it) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. |  | Not verified in current zip | Pending |  | Low
Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. |  | Verified in current zip (match: study, custom, unsure) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/BRANDING_NOTE.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json | High
In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. |  | Not verified in current zip | Pending |  | Low
1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) |  | Verified in current zip (match: active, unsure) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. |  | Verified in current zip (match: active, relearn) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text |  | Not verified in current zip | Pending |  | Low
In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. |  | Verified in current zip (match: buttons) | Done | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/0d881caa5ee8/progress.json; KenpoFlashcardsWebServer/data/users/1cc70e61cd9e/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | High
If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. |  | Not verified in current zip | Done |  | Low
Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. |  | Not verified in current zip | Done |  | Low
If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. |  | Not verified in current zip | Pending |  | Low
Saved breakdown text below "Select group..." dropdown does not change on changing cards |  | Verified in current zip (match: select group...) | Done | KenpoFlashcardsWebServer/static/index.html | High
As admin>Stats: to see who is actively/recently logged in and studying |  | Not verified in current zip | Pending |  | Low
Notes to be added to cards, to view if selected. Option to share and collaberate with others. |  | Not verified in current zip | Pending |  | Low
Next thing is to add png image and to change the color a little to match the company colors |  | Not verified in current zip | Pending |  | Low
Run as service |  | Not verified in current zip | Pending |  | Low
and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app. |  | Not verified in current zip | Pending |  | Low

## Optimized Grouping
Category | Android: Pending (missing) | Web: Pending (missing) | Sync gaps (Done in one, Pending in other) | Notes / Suggested order
Fixes | • In portrait, "Learned" and "All Cards" and "Custom" page Title bar needs to match "Unsure" and "To Study" pages font size and search funtion. In "Learned">"List" and "Study", remove the redundant status count i.e. "Learned:##" below the other status Counts. On custom page move "Custom:##" in line with the other statuses to the right of "Learned:##" • In landscape, "Learned">"Study" page needs to match "To Study" and "Unsure" page format design, • In landscape, when search bar opens from spy glass, the text "Search" is cut in half, make text smaller to be seen in box. • In landscape, There is unused background space, that can be filled by making cards longer . • In both orientations, remove Search bar in all decks; "To Study" (done), "Unsure" (done), "Learned">"List", "Learned">"Study" (Lanscape done, portrait pending), "All" (Lanscape done, portrait pending), "Custom" (Lanscape done, portrait pending); replace with Spy Glass Icon. • Make "Learned">"Study" look like other study decks. • In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. • Saved breakdown text below "Select group..." dropdown does not change on changing cards • In "Custom" set status, I dont want the "To Study:###","To Unsure:###","Learned:###" number to reflect the main decks status, but only the custom sets status. When we select "To Study:###","To Unsure:###","Learned:###" only in custom page it will go to that a custom version of "Unsure" and custom "Learned", custom "Custom:##". "Custom:##" will show all cards in the Customs set. While in custom page when we tap an action(got it, unsure, learned), cards will only be changed in the custom page not in any main decks or status. Add a Toggle setting Only in Custom page that will push custom Status to main deck if user wants, so when learned in custom deck it will be reflected in main decks. • In Custom page, change trash icon function to remove that card only, after confirmation. Change "Remove" button to "Unsure" to move cards to customs Unsure Deck.
Admin & Auth | • Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. • If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" • As admin>Stats: to see who is actively/recently logged in and studying | • Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. • Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. • If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" • "Key Accepted" should show on either project only if key is valid showing invalid if it isnt • Move Logout/Login button into "User: ********" • As admin>Stats: to see who is actively/recently logged in and studying | • Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. (App: Done, Web: Pending) • "Key Accepted" should show on either project only if key is valid showing invalid if it isnt (App: Done, Web: Pending) | 1) Stabilize authentication/admin gating first (affects sync, logs, admin tools).
Logs & Monitoring | • (None) | • (None) | • (None) | 2) Add observability next (logs + download/reset) to debug remaining work safely.
Search & Navigation | • Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it • In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. • Saved breakdown text below "Select group..." dropdown does not change on changing cards | • Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it • In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. • 4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text | • 4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text (App: Done, Web: Pending) • Saved breakdown text below "Select group..." dropdown does not change on changing cards (App: Pending, Web: Done) | 3) Polish navigation/search UX (low risk, high QoL).
Sync & Data | • (None) | • (None) | • (None) | 6) Sync/version/data schema changes after UI is stable (higher coordination cost).
Voice & Accessibility | • Setting to set to speak on both term and pronunciation | • Setting to set to speak on both term and pronunciation | • (None) | 8) Voice tweaks can be done anytime but are usually low dependency.
Other | • a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) • c.) Add option to Change between Study subject flashcards via json files (manually or AI created) • Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. • If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. • Notes to be added to cards, to view if selected. Option to share and collaberate with others. | • a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) • c.) Add option to Change between Study subject flashcards via json files (manually or AI created) • Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. • If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. • Notes to be added to cards, to view if selected. Option to share and collaberate with others. • Next thing is to add png image and to change the color a little to match the company colors • Run as service • and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app. | • (None) | Bucket for items that don’t match above categories.

## Implemented Changes
Date | Project | Version | Build | Implemented items (Done)
2026-01-15 | Android App | 4.4.2 | 22 | • When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. • In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). • Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. • "Key Accepted" should show on either project only if key is valid showing invalid if it isnt • Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. • 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. • In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. • Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} • In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. • Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. • 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) • Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. • 4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text • In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right.
2026-01-15 | Web Server | 5.5.2 | 29 | • When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. • Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. • 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. • In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. • Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} • In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. • Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. • 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) • Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. • In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. • Saved breakdown text below "Select group..." dropdown does not change on changing cards

## Android Feature Inventory
Category | Type | Feature | Primary Source | Evidence files
🃏 Flash Card Learning | Feature (README) | Vocabulary terms displayed on interactive flash cards | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🃏 Flash Card Learning | Feature (README) | Tap to flip between term and definition | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🃏 Flash Card Learning | Feature (README) | Swipe navigation between cards | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🃏 Flash Card Learning | Feature (README) | Smooth flip animations for intuitive study | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🃏 Flash Card Learning | Feature (README) | Pronunciation display for terms with phonetic guides | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🃏 Flash Card Learning | Feature (README) | Reverse mode - study definition-first | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
📂 Three-State Progress Tracking | Feature (README) | To Study - Active cards you're learning | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
📂 Three-State Progress Tracking | Feature (README) | Unsure - Cards you're uncertain about | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
📂 Three-State Progress Tracking | Feature (README) | Learned - Cards you've mastered | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
⭐ Custom Study Sets | Feature (README) | Star any card to add it to your Custom Set | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
⭐ Custom Study Sets | Feature (README) | Create personalized review decks | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/Models.kt
⭐ Custom Study Sets | Feature (README) | Access starred cards from any screen | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
⭐ Custom Study Sets | Feature (README) | Perfect for test prep or belt reviews | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt
📊 Term Breakdowns | Feature (README) | Breakdown editor for each term | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt
📊 Term Breakdowns | Feature (README) | Split compound terms into parts (e.g., TaeKwonDo → Tae, Kwon, Do) | README.md | app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; README.md
📊 Term Breakdowns | Feature (README) | Add meanings for each part | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt
📊 Term Breakdowns | Feature (README) | Include literal translations and notes | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt
📊 Term Breakdowns | Feature (README) | Auto-split feature detects word boundaries | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
📊 Term Breakdowns | Feature (README) | AI-powered autofill (ChatGPT or Gemini) | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🔍 Filtering & Sorting | Feature (README) | Group filter - Study cards from specific categories | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/StudySettings.kt
🔍 Filtering & Sorting | Feature (README) | Search - Find cards by term, definition, or pronunciation | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🔍 Filtering & Sorting | Feature (README) | 5 sort modes: | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt
🔍 Filtering & Sorting | Feature (README) | Original order | README.md | app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🔍 Filtering & Sorting | Feature (README) | Alphabetical (A-Z) | README.md | app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🔍 Filtering & Sorting | Feature (README) | Groups (alphabetical) | README.md | app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🔍 Filtering & Sorting | Feature (README) | Groups (random order) | README.md | app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🔍 Filtering & Sorting | Feature (README) | Random | README.md | app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; app/src/main/java/com/example/kenpoflashcards/Store.kt
🔊 Text-to-Speech | Feature (README) | Speak button reads terms aloud | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🔊 Text-to-Speech | Feature (README) | Adjustable speech rate (0.5x - 2.0x) | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt
🔊 Text-to-Speech | Feature (README) | Pronunciation-only mode - speaks just the phonetic pronunciation when available | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
📱 Responsive Design | Feature (README) | Full landscape mode support with side-by-side layout | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
📱 Responsive Design | Feature (README) | Adaptive UI for different screen sizes | README.md | README.md; app/src/main/res/mipmap-anydpi-v26/ic_launcher_round.xml
📱 Responsive Design | Feature (README) | Dark theme throughout | README.md | README.md; app/src/main/res/values/colors.xml
☁️ Web App Sync (v4.0+) | Feature (README) | Login to sync with web app server | README.md | app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; app/src/main/java/com/example/kenpoflashcards/StudySettings.kt
☁️ Web App Sync (v4.0+) | Feature (README) | Push/Pull progress between devices | README.md | app/src/main/java/com/example/kenpoflashcards/Repository.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
☁️ Web App Sync (v4.0+) | Feature (README) | Sync breakdowns from shared database | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt
☁️ Web App Sync (v4.0+) | Feature (README) | First login auto-sync - always syncs on first device login (v4.4.0+) | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
☁️ Web App Sync (v4.0+) | Feature (README) | Auto-sync settings - auto-pull on future logins, auto-push on change | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
☁️ Web App Sync (v4.0+) | Feature (README) | API keys pulled for all users - AI features available to everyone (v4.4.2+) | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
☁️ Web App Sync (v4.0+) | Feature (README) | Server: sidscri.tplinkdns.com:8009 | README.md | app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
☁️ Web App Sync (v4.0+) | Feature (README) | Endpoint: POST /api/sync/login (token-based auth) | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt
🤖 AI Integration (v4.0+) | Feature (README) | ChatGPT API integration for breakdown autofill | README.md | README.md; CHANGELOG.md
🤖 AI Integration (v4.0+) | Feature (README) | Gemini API integration (v4.2.0+) | README.md | README.md; CHANGELOG.md
🤖 AI Integration (v4.0+) | Feature (README) | Model selection - choose gpt-4o, gpt-4o-mini, gemini-1.5-flash, etc. (v4.3.0+) | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
🤖 AI Integration (v4.0+) | Feature (README) | Key validation indicators - shows "Key Accepted" or "Key Invalid" (v4.4.0+) | README.md | README.md; CHANGELOG.md
🤖 AI Integration (v4.0+) | Feature (README) | Shared API keys - All users receive API keys on login (v4.4.2+) | README.md | README.md; CHANGELOG.md
🤖 AI Integration (v4.0+) | Feature (README) | Automatically generates: | README.md | README.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
🤖 AI Integration (v4.0+) | Feature (README) | Term part splits | README.md | app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; README.md
🤖 AI Integration (v4.0+) | Feature (README) | Part meanings/translations | README.md | app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; README.md
🤖 AI Integration (v4.0+) | Feature (README) | Literal translations | README.md | app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; README.md
👤 Admin Features (v4.2.0+) | Feature (README) | Admin-only access - Admin Settings visible only to admin users | README.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
👤 Admin Features (v4.2.0+) | Feature (README) | (Admin) label - Shows after username when logged in as admin (v4.4.0+) | README.md | README.md; CHANGELOG.md
👤 Admin Features (v4.2.0+) | Feature (README) | API key management - Push/pull encrypted keys to/from server | README.md | app/src/main/java/com/example/kenpoflashcards/Repository.kt; README.md
👤 Admin Features (v4.2.0+) | Feature (README) | Server-based admin list - Admin usernames fetched from server Source of Truth (v4.3.0+) | README.md | README.md; CHANGELOG.md
Added | Change (CHANGELOG) | Deck Management groundwork: Data models and storage for future multi-deck support | CHANGELOG.md | CHANGELOG.md; README.md
Added | Change (CHANGELOG) | StudyDeck model with id, name, description, isDefault, isBuiltIn flags | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/Store.kt
Added | Change (CHANGELOG) | DeckSettings for tracking active deck selection | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/StudySettings.kt
Added | Change (CHANGELOG) | Storage methods for decks and user-created cards | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/Store.kt
Added | Change (CHANGELOG) | "Manage Decks (Coming Soon)" placeholder button in Settings | CHANGELOG.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; CHANGELOG.md
Removed | Change (CHANGELOG) | Import CSV button: Replaced with future Deck Management feature | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/Store.kt
Removed | Change (CHANGELOG) | "Show Custom Set Button" setting: Unnecessary setting removed | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/StudySettings.kt
Fixed | Change (CHANGELOG) | Custom Set settings dialog: "Reflect status in Main Decks" toggle wraps properly | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
Fixed | Change (CHANGELOG) | Custom Set "ALL" filter: Shows all cards (was incorrectly filtering) | CHANGELOG.md | CHANGELOG.md; README.md
Fixed | Change (CHANGELOG) | Custom Set status counts: Increased height/font to prevent text cutoff | CHANGELOG.md | CHANGELOG.md; app/src/main/java/com/example/kenpoflashcards/MainActivity.kt
Fixed | Change (CHANGELOG) | Custom Set Learned view: Shows "Relearn" button instead of "Got it" | CHANGELOG.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; CHANGELOG.md
Changed | Change (CHANGELOG) | API keys auto-pull on login: Progress and API keys sync automatically | CHANGELOG.md | app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; README.md
Changed | Change (CHANGELOG) | Push/Pull buttons restored: Manual sync available in Sync Progress screen | CHANGELOG.md | CHANGELOG.md; README.md
Settings | Setting Flag | Setting: selectedGroup | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: selectedSubgroup | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: studyFilterGroup (null = All Cards) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: sortMode | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: randomize | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showGroup | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showSubgroup | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: reverseCards | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: randomizeUnlearned | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: randomizeUnsure | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: randomizeLearnedStudy | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: linkRandomizeTabs | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showBreakdownOnDefinition | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showDefinitionsInAllList | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showDefinitionsInLearnedList | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showLearnedListGroupLabel | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showUnlearnedUnsureButtonsInAllList | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showRelearnUnsureButtonsInLearnedList | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: learnedViewMode | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: speechVoice | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: speechRate | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: speakPronunciationOnly (Default OFF per screenshot) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: filterGroup | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: customSetSettings | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showCustomSetButton | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: randomOrder | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showGroupLabel | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showBreakdown | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showDefinitions | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: showActionButtons | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: reflectInMainDecks (If true, status changes affect main decks too) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: webAppUrl | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: authToken | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: username | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: isLoggedIn | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: lastSyncTime | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: chatGptApiKey | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: chatGptEnabled | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: chatGptModel (Default model) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: geminiApiKey | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: geminiEnabled | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: geminiModel (Default model) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: autoPullOnLogin | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: autoPushOnChange | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: pendingSync (True if changes made while offline) | StudySettings.kt | StudySettings.kt
Settings | Setting Flag | Setting: breakdownAiChoice | StudySettings.kt | StudySettings.kt
Sync/API | Client Endpoint | API call: /api/admin/apikeys | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/admin/users | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/breakdowns | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/login | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/profile | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/apikeys | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/breakdowns | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/customset | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/login | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/pull | WebAppSync.kt | WebAppSync.kt
Sync/API | Client Endpoint | API call: /api/sync/push | WebAppSync.kt | WebAppSync.kt

## WebServer Feature Inventory
Category | Type | Feature | Primary Source | Evidence files
What It Does | Feature (README) | Authentication - User login with token-based Android sync | README.md | README.md; app.py
What It Does | Feature (README) | Progress Sync - Push/pull card progress between devices | README.md | static/user-guide.html; app.py
What It Does | Feature (README) | Breakdown Sync - Shared term breakdown database | README.md | app.py; README.md
What It Does | Feature (README) | Web UI - Browser-based flashcard interface | README.md | README.md; static/app.js
What It Does | Feature (README) | Helper Mapping - Canonical card IDs for cross-device consistency | README.md | app.py; README.md
What It Does | Feature (README) | AI Integration - ChatGPT and Gemini API for breakdown autofill | README.md | README.md; static/ai-access.html
What It Does | Feature (README) | Encrypted API Keys - Secure storage shared between Android and web | README.md | app.py; README.md
What It Does | Feature (README) | Shared API Keys - All authenticated users can pull API keys (v5.5.2+) | README.md | app.py; README.md
What It Does | Feature (README) | Admin Management - Centralized admin users Source of Truth | README.md | README.md; app.py
Added | Change (CHANGELOG) | **Version/docs sync with Android App 4.4.2 (v22) | CHANGELOG.md | version.json; CHANGELOG.md
Changed | Change (CHANGELOG) | No functional server code changes in this patch release. | CHANGELOG.md | CHANGELOG.md; version.json
API | API Endpoint | API endpoint: / | app.py | app.py
API | API Endpoint | API endpoint: /.well-known/security.txt | app.py | app.py
API | API Endpoint | API endpoint: /<path:filename> | app.py | app.py
API | API Endpoint | API endpoint: /about | app.py | app.py
API | API Endpoint | API endpoint: /admin | app.py | app.py
API | API Endpoint | API endpoint: /api/admin/apikeys | app.py | app.py
API | API Endpoint | API endpoint: /api/admin/status | app.py | app.py
API | API Endpoint | API endpoint: /api/admin/users | app.py | app.py
API | API Endpoint | API endpoint: /api/ai | app.py | app.py
API | API Endpoint | API endpoint: /api/breakdown | app.py | app.py
API | API Endpoint | API endpoint: /api/breakdown_autofill | app.py | app.py
API | API Endpoint | API endpoint: /api/breakdowns | app.py | app.py
API | API Endpoint | API endpoint: /api/bulk_set_status | app.py | app.py
API | API Endpoint | API endpoint: /api/cards | app.py | app.py
API | API Endpoint | API endpoint: /api/counts | app.py | app.py
API | API Endpoint | API endpoint: /api/groups | app.py | app.py
API | API Endpoint | API endpoint: /api/health | app.py | app.py
API | API Endpoint | API endpoint: /api/login | app.py | app.py
API | API Endpoint | API endpoint: /api/logout | app.py | app.py
API | API Endpoint | API endpoint: /api/me | app.py | app.py
API | API Endpoint | API endpoint: /api/register | app.py | app.py
API | API Endpoint | API endpoint: /api/reset | app.py | app.py
API | API Endpoint | API endpoint: /api/set_status | app.py | app.py
API | API Endpoint | API endpoint: /api/settings | app.py | app.py
API | API Endpoint | API endpoint: /api/settings_reset | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/apikeys | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/breakdowns | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/customset | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/helper | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/login | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/pull | app.py | app.py
API | API Endpoint | API endpoint: /api/sync/push | app.py | app.py
API | API Endpoint | API endpoint: /api/version | app.py | app.py
API | API Endpoint | API endpoint: /api/web/admin/apikeys | app.py | app.py
API | API Endpoint | API endpoint: /api/whoami | app.py | app.py
API | API Endpoint | API endpoint: /favicon.ico | app.py | app.py
API | API Endpoint | API endpoint: /robots.txt | app.py | app.py
API | API Endpoint | API endpoint: /sitemap.xml | app.py | app.py
API | API Endpoint | API endpoint: /user-guide | app.py | app.py
API | API Endpoint | API endpoint: /user-guide.pdf | app.py | app.py

## Feature Differences
Diff Type | Item | Android | WebServer | How to implement / port | Evidence (Android) | Evidence (WebServer)
API | /api/profile | Yes (Android calls) | No (Server missing) | Add this endpoint in app.py OR remove/replace Android call in WebAppSync.kt. Check expected response schema. | WebAppSync.kt
API | /api/admin/status | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/ai | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/breakdown | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/breakdown_autofill | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/bulk_set_status | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/cards | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/counts | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/groups | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/health | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/logout | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/me | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/register | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/reset | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/set_status | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/settings | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/settings_reset | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/sync/helper | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/version | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/web/admin/apikeys | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
API | /api/whoami | No (Android doesn't call) | Yes (Server has) | If Android should use this, add a WebAppSync.kt method + UI hook; otherwise ignore (web UI / admin feature). |  | app.py
README Feature | Vocabulary terms displayed on interactive flash cards | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Tap to flip between term and definition | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Swipe navigation between cards | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Smooth flip animations for intuitive study | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Pronunciation display for terms with phonetic guides | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Reverse mode - study definition-first | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | To Study - Active cards you're learning | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Unsure - Cards you're uncertain about | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Learned - Cards you've mastered | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Star any card to add it to your Custom Set | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Create personalized review decks | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Access starred cards from any screen | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Perfect for test prep or belt reviews | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Breakdown editor for each term | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Split compound terms into parts (e.g., TaeKwonDo → Tae, Kwon, Do) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Add meanings for each part | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Include literal translations and notes | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Auto-split feature detects word boundaries | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | AI-powered autofill (ChatGPT or Gemini) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Group filter - Study cards from specific categories | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Search - Find cards by term, definition, or pronunciation | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | 5 sort modes: | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Original order | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Alphabetical (A-Z) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Groups (alphabetical) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Groups (random order) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Random | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Speak button reads terms aloud | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Adjustable speech rate (0.5x - 2.0x) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Pronunciation-only mode - speaks just the phonetic pronunciation when available | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Full landscape mode support with side-by-side layout | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Adaptive UI for different screen sizes | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Dark theme throughout | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Login to sync with web app server | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | First login auto-sync - always syncs on first device login (v4.4.0+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Auto-sync settings - auto-pull on future logins, auto-push on change | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | API keys pulled for all users - AI features available to everyone (v4.4.2+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Server: sidscri.tplinkdns.com:8009 | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Endpoint: POST /api/sync/login (token-based auth) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Model selection - choose gpt-4o, gpt-4o-mini, gemini-1.5-flash, etc. (v4.3.0+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Key validation indicators - shows "Key Accepted" or "Key Invalid" (v4.4.0+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Automatically generates: | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Term part splits | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Part meanings/translations | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Literal translations | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Admin-only access - Admin Settings visible only to admin users | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | (Admin) label - Shows after username when logged in as admin (v4.4.0+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | API key management - Push/pull encrypted keys to/from server | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Server-based admin list - Admin usernames fetched from server Source of Truth (v4.3.0+) | Yes (Android README) | Not listed in WebServer README | If you want parity on web UI, implement in web client (templates/static JS). If it requires sync, add/update server endpoint and persist in data/. | README.md
README Feature | Authentication - User login with token-based Android sync | Not listed in Android README | Yes (WebServer README) | If you want parity on Android, add UI/logic in Android app; if server-only, document it under Web App Sync section. |  | README.md
README Feature | Web UI - Browser-based flashcard interface | Not listed in Android README | Yes (WebServer README) | If you want parity on Android, add UI/logic in Android app; if server-only, document it under Web App Sync section. |  | README.md
README Feature | Helper Mapping - Canonical card IDs for cross-device consistency | Not listed in Android README | Yes (WebServer README) | If you want parity on Android, add UI/logic in Android app; if server-only, document it under Web App Sync section. |  | README.md
README Feature | Encrypted API Keys - Secure storage shared between Android and web | Not listed in Android README | Yes (WebServer README) | If you want parity on Android, add UI/logic in Android app; if server-only, document it under Web App Sync section. |  | README.md
README Feature | Admin Management - Centralized admin users Source of Truth | Not listed in Android README | Yes (WebServer README) | If you want parity on Android, add UI/logic in Android app; if server-only, document it under Web App Sync section. |  | README.md