## List with Pending or Done
Change Request | Category | Android Status | Web Status
Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. |  | Pending | Pending
User dropdown with version, Admin button, About page with creator info (Sidney Shelton, Sidscri@yahoo.com), User Guide |  | Done | Done
Add Web App Sync section into Sync Progress page within User menu for sync status history |  | Done | Pending
About page with version, creator contact, feature overview, downloadable User Guide |  | Done | Done
Login page separated from Admin Settings, Login button replaces Admin Settings for non-admins |  | Done | Done
ChatGPT and Gemini API in admin, auto-pull progress/breakdowns on login, auto-sync settings |  | Done | Done
If admin is logged in add (Admin) after username display |  | Done | Pending
Key Accepted/Invalid validation for API keys |  | Done | Pending
Gemini API integration with encrypted key storage, Choose Breakdown AI selector |  | Done | Done
Breakdown AI service selector (Auto Select, ChatGPT, Gemini) in Sync Breakdowns section |  | Done | Done
Admin page with stats, user list, password reset, logging |  | Done | Done
Remove old Logout button (consolidate to user menu) |  | Pending | Pending
Multiple choice study mode option per deck |  | Done | Done
Setting to speak both term and pronunciation |  | Pending | Pending
Custom deck with star functionality, Custom-only status (isolated from main decks) |  | Done | Done
Admin-generated static card deck feature |  | Done | Done
Manual term/definition adding with AI-generated content |  | Pending | Pending
CSV/document/image import for creating flashcard sets with AI processing |  | Done | Done
Switch between different flashcard JSON subjects |  | Pending | Pending
Reshuffle icon (⟳) when Random order is ON |  | Done | Done
Remove redundant top bar/page title (search icon based) |  | Done | Done
Custom page isolated status (Custom:##, Unsure:##, Learned:##) |  | Done | Done
Custom page settings isolated from global settings |  | Done | Done
Remove button in Custom changed to Unsure, remove icon removes single card |  | Done | Done
Dice button for random # of unlearned cards in Custom |  | Done | Pending
Search icon instead of search bar in all decks |  | Done | Done
Search X to clear, tap outside exits search but keeps results |  | Done | Pending
All page button spacing fixed (Active/Unsure not smooshed) |  | Done | Done
Rename Active to Relearn, status Active to To Learn, Reset to Default Settings |  | Done | Done
Landscape layout - remove bottom status text in Learned/All pages |  | Pending | Pending
Landscape improvements - fill page space, status bar colors |  | Done | Done
Bidirectional sync with timestamp-based conflict resolution |  | Done | Done
Speak term option (press speak to listen), speak definition on flip |  | Done | Done
End of Deck card with Tap to Return to Top |  | Done | Done
Breakdown data icon indicator on cards with quick view |  | Pending | Pending
Breakdown text updates when changing cards (dropdown selection) |  | Pending | Pending
Admin stats - who is actively/recently logged in |  | Pending | Pending
Notes on cards with sharing/collaboration option |  | Pending | Pending
PNG image and company colors branding |  | Pending | Done
Run as Windows service with tray icon |  | N/A | Pending

## Android app updates Status
Change Request | Status | Evidence | Notes
User dropdown with version, Admin button, About page | Done | MainActivity.kt: AboutScreen, UserGuideScreen; CHANGELOG.md v4.2.0
Sync Progress page with Push/Pull | Done | MainActivity.kt: SyncProgressScreen; CHANGELOG.md v4.2.0
About page with creator info, User Guide | Done | MainActivity.kt: AboutScreen, UserGuideScreen
Login page separated from Admin | Done | MainActivity.kt: LoginScreen, Route.Login; CHANGELOG.md v4.2.0
ChatGPT and Gemini API, auto-sync | Done | ChatGptHelper.kt, GeminiHelper.kt, WebAppSync.kt; CHANGELOG.md v4.2.0+
(Admin) label after username | Done | MainActivity.kt: adminLabel variable, lines 1108, 1225, 1355
Key Accepted/Invalid validation | Done | MainActivity.kt: Key validation UI; CHANGELOG.md v4.4.0
Gemini API with Choose Breakdown AI | Done | GeminiHelper.kt; StudySettings.kt: breakdownAiService
Breakdown AI selector | Done | StudySettings.kt: BreakdownAiService enum; MainActivity.kt: AI picker
Admin page with user management | Done | MainActivity.kt: AdminScreen; CHANGELOG.md v4.3.0
Multiple choice study mode | Done | StudySettings.kt: studyMode; MainActivity.kt: StudyMode enum
Custom deck with star | Done | Models.kt: isInCustomSet; Store.kt: customSet; CHANGELOG.md
Admin-generated deck | Done | Store.kt: curatedSet; CHANGELOG.md v4.2.0+
CSV import | Done | CsvImport.kt; CHANGELOG.md
Reshuffle icon | Done | README.md v4.4.2: ⟳ Reshuffle icon | Per changelog - verify in UI
Remove redundant top bar | Done | CHANGELOG.md v4.4.2: compact header row
Custom isolated status | Done | Store.kt: CustomCardStatus; StudySettings.kt: CustomSetSettings
Custom settings isolated | Done | StudySettings.kt: CustomSetSettings class
Remove→Unsure in Custom | Done | CHANGELOG.md v4.4.2; MainActivity.kt
Dice random cards | Done | CHANGELOG.md v4.4.2: 🎲 random Unlearned cards for Custom Set
Search icon toggle | Done | MainActivity.kt: expandSearch; CHANGELOG.md v4.4.2
Search X clear, tap outside | Done | CHANGELOG.md v4.4.2: X icon to clear, tap outside closes
All page buttons fixed | Done | CHANGELOG.md v4.0.1
Rename Active→Relearn | Done | CHANGELOG.md v4.0.1, v3.0.1: Renamed Unlearned to To Study
Landscape improvements | Done | CHANGELOG.md v4.0.0: Landscape mode support
Bidirectional sync | Done | WebAppSync.kt: timestamp logic; Repository.kt
Speak term/definition options | Done | TtsHelper.kt; StudySettings.kt: pronunciationOnly
End of Deck return to top | Done | CHANGELOG.md v4.2.0: Return-to-top navigation
Server log in admin settings | Pending | Not found in codebase | Future feature
Remove old Logout button | Pending | Logout button still exists | Consolidate to user menu
Speak both term and pronunciation | Pending | TtsHelper supports one at a time | Need dual speak option
Manual term adding with AI | Pending | No UI for adding terms | Future feature
Switch JSON subjects | Pending | Single JSON file supported | Multi-subject support needed
Landscape remove bottom status | Pending | Still shows in some views | Layout refinement
Breakdown icon indicator | Pending | No visual indicator on cards | UI enhancement
Breakdown text updates on card change | Pending | Dropdown may not update | Bug fix
Admin stats (active users) | Pending | No active user tracking UI | Admin enhancement
Notes on cards | Pending | No notes feature | Future feature
PNG/company colors | Pending | Using default launcher icon | Branding update

## Web Server updates Status
Change Request | Status | Evidence | Notes
User dropdown, Admin button, About page | Done | about.html, admin.html, app.js: userDropdown
About page with creator, User Guide | Done | about.html: Sidney Shelton; user-guide.html
Login page | Done | app.py: /api/login, /api/sync/login; index.html
ChatGPT and Gemini API, auto-sync | Done | app.py: openai, gemini endpoints; CHANGELOG.md v5.4.0+
Gemini API with selector | Done | ai-access.html; app.py: gemini integration
Breakdown AI selector | Done | app.js: aiService dropdown; app.py
Admin page | Done | admin.html; app.py: admin endpoints
Multiple choice mode | Done | index.html, app.js: quiz mode support
Custom deck with star | Done | app.js: customSet; index.html: star button
Admin-generated deck | Done | app.js: curatedSet; app.py
Document import | Done | app.py: file upload handling
Reshuffle icon | Done | index.html: randomRefreshBtn ⟳; app.js
Remove top bar | Done | styles.css, app.js: studyHeaderRow compact
Custom isolated status | Done | app.js: customStatus tracking
Custom settings isolated | Done | app.js: customSetSettings
Remove→Unsure in Custom | Done | app.js: Custom unsure button; CHANGELOG.md
Search icon toggle | Done | index.html: searchBtn; app.js: showSearch
Search clear, tap outside | Done | app.js: closeSearch function
Buttons fixed | Done | styles.css: button spacing
Rename Active→Relearn | Done | app.js: To Study, Relearn labels
Bidirectional sync | Done | app.py: timestamp handling; CHANGELOG.md v5.2.0
End of Deck return | Done | index.html, app.js: scrollToTop
Breakdown indicator | Done | app.js: breakdown display
Breakdown updates on card | Done | app.js: loadBreakdown on card change
PNG/favicon | Done | favicon.ico present
Server log in admin | Pending | Basic logging exists but no admin UI tabs | Add log viewer UI
Sync Progress page UI | Pending | Sync endpoints exist, no dedicated UI page | Port from Android
(Admin) label after username | Pending | isAdminUser() exists but no label display | UI enhancement
Key Accepted/Invalid | Pending | No validation display in ai-access.html | Add validation UI
Remove old Logout button | Pending | Logout in user menu exists | Clean up
Speak term and pronunciation | Pending | Basic TTS only | Dual speak option
Manual term adding | Pending | No add term UI | Future feature
Switch JSON subjects | Pending | Single JSON | Multi-subject
Dice random Custom | Pending | No random picker in Custom | Port from Android
Landscape status text | Pending | May still show | Layout fix
Admin stats | Pending | No active user UI | Admin enhancement
Notes on cards | Pending | No notes feature | Future feature
Run as service | Pending | Batch file launch only | Windows service needed

## Optimized Grouping
Priority | Category | Android Pending | Web Pending | Sync Gaps | Recommended Order
1-Critical | Fixes/Repairs | • Landscape remove bottom status text • Breakdown text not updating on card change | • (Admin) label after username • Key Accepted/Invalid validation • Landscape layout improvements | • Android Done, Web Pending: (Admin) label, Key validation, Search tap-outside behavior, Dice random Custom | Fix bugs first before adding features
2-High | Admin & Auth | • Server log viewer UI with tabs • Admin stats (active users) | • Server log viewer UI • Sync Progress page UI • Admin stats | • Web missing: Sync Progress dedicated page | Add observability for debugging
3-Medium | UI Polish | • Remove old Logout button | • Remove old Logout button • Landscape status text removal | • Both pending: Old Logout button removal | UX consistency
4-Medium | Voice/TTS | • Speak both term and pronunciation setting | • Speak both term and pronunciation | • Both pending | Low dependency, can do anytime
5-Low | New Features | • Manual term adding with AI • Switch JSON subjects • Notes on cards • PNG/branding | • Manual term adding • Switch JSON subjects • Notes on cards • Run as service | • Both pending on most new features | After core features stable

## Implemented Changes
Date | Project | Version | Build | Implemented Items
2026-01-14 | Android App | 4.4.2 | 22 | • Settings toggle to show/hide Custom Set button • Portrait search icon-based (matches landscape) • (Admin) label after username • Tap outside search closes but keeps results • X icon to clear search • Random checkbox beside Card #/## • ⟳ Reshuffle icon • Custom Set uses own settings • 🎲 Pick random Unlearned cards for Custom
2026-01-14 | Web Server | 5.5.2 | 29 | • Version/docs sync with Android 4.4.2 • Login regression fix for admin users • Case-insensitive login • Logs panel requires admin session (not localhost)

## Android Features
Feature | Status | Version Added | Files
Flash Card Learning with flip animation | Done | 1.0.0 | MainActivity.kt
Three-State Progress (To Study/Unsure/Learned) | Done | 2.0.0 | Models.kt, Store.kt
Custom Study Sets (star cards) | Done | 2.2.0 | Store.kt, Models.kt
Term Breakdowns with AI autofill | Done | 2.0.0 | ChatGptHelper.kt, GeminiHelper.kt
Group Filtering & 5 Sort Modes | Done | 2.2.0 | StudySettings.kt
Text-to-Speech with rate control | Done | 2.0.0 | TtsHelper.kt
Landscape Mode Support | Done | 4.0.0 | MainActivity.kt
Web App Sync (Login/Push/Pull) | Done | 4.0.0 | WebAppSync.kt, Repository.kt
ChatGPT API Integration | Done | 4.0.0 | ChatGptHelper.kt
Gemini API Integration | Done | 4.2.0 | GeminiHelper.kt
Model Selection (gpt-4o, gemini-1.5-flash) | Done | 4.3.0 | StudySettings.kt
About Screen with Creator Info | Done | 4.2.0 | MainActivity.kt
User Guide Screen (printable) | Done | 4.2.0 | MainActivity.kt
Dedicated Login Screen | Done | 4.2.0 | MainActivity.kt
Sync Progress Screen | Done | 4.2.0 | MainActivity.kt
Breakdown AI Selector | Done | 4.2.0 | StudySettings.kt
Auto-sync on first login | Done | 4.4.0 | WebAppSync.kt
(Admin) label for admin users | Done | 4.4.0 | MainActivity.kt
Key Accepted/Invalid indicators | Done | 4.4.0 | MainActivity.kt
API keys for all users | Done | 4.4.1 | WebAppSync.kt
Portrait search icon toggle | Done | 4.4.2 | MainActivity.kt
Random checkbox + Reshuffle icon | Done | 4.4.2 | MainActivity.kt
Custom Set isolated settings | Done | 4.4.2 | StudySettings.kt
🎲 Random Unlearned picker for Custom | Done | 4.4.2 | MainActivity.kt
CSV Import | Done | 3.0+ | CsvImport.kt
Dark Theme | Done | 2.0.0 | themes.xml

## Web Server Features
Feature | Status | Version Added | Files
Web-based Flashcard UI | Done | 1.0.0 | index.html, app.js
User Authentication (session + token) | Done | 4.0.0 | app.py
Progress Sync API | Done | 5.0.0 | app.py
Breakdown Sync API | Done | 5.0.0 | app.py
Helper ID Mapping | Done | 5.0.0 | app.py
ChatGPT API Integration | Done | 4.2.0 | app.py
Gemini API Integration | Done | 5.4.0 | app.py
Encrypted API Key Storage | Done | 5.4.0 | app.py
Model Selection UI | Done | 5.5.0 | ai-access.html
Admin Users Source of Truth | Done | 5.5.0 | admin_users.json
API Keys for All Users | Done | 5.5.1 | app.py
About Page | Done | 5.3.0 | about.html
Admin Diagnostics Page | Done | 5.3.0 | admin.html
User Guide Page | Done | 5.3.0 | user-guide.html
User Dropdown Menu | Done | 5.3.0 | app.js
Version API Endpoint | Done | 5.3.0 | app.py, version.json
Custom Study Sets | Done | 4.2.0 | app.js
Multiple Choice Mode | Done | 4.2.0 | app.js
Group Filtering | Done | 4.2.0 | app.js
Search with Icon Toggle | Done | 5.0+ | app.js, index.html
Reshuffle Button (⟳) | Done | 5.0+ | index.html, app.js
Dark Theme | Done | 4.0.0 | styles.css
Favicon | Done | 5.1.1 | favicon.ico
Security.txt | Done | 5.1.1 | .well-known/security.txt

## Feature Comparison
Feature | Android | Web Server | Gap | Recommendation
(Admin) label after username | Done | Pending | Web missing | Add to app.js: show (Admin) in user menu when isAdminUser()
Key Accepted/Invalid validation | Done | Pending | Web missing | Add validation display in ai-access.html, test API key on input
Sync Progress dedicated page | Done | Pending | Web missing | Create sync-progress.html with Push/Pull buttons and status
🎲 Random Unlearned picker for Custom | Done | Pending | Web missing | Add dice icon button in Custom settings, prompt for count
Search tap-outside keeps results | Done | Pending | Web missing | Modify closeSearch() in app.js to not clear searchQuery
Speak both term and pronunciation | Pending | Pending | Both missing | Add dual TTS option in settings
Server log viewer UI | Pending | Pending | Both missing | Create logs UI in admin page with tabs for server/error/user logs
Manual term adding | Pending | Pending | Both missing | Create Add Term dialog with AI-assist options
Switch JSON subjects | Pending | Pending | Both missing | Add subject selector dropdown, load different JSON files
Notes on cards | Pending | Pending | Both missing | Add notes field to card model, editor UI, sync support
Admin stats (active users) | Pending | Pending | Both missing | Track last activity timestamp, display in admin page
Windows service | N/A | Pending | Web only | Use NSSM or create Windows service wrapper
Reshuffle icon (⟳) | Done | Done | Both done | ✓ Synced
Custom isolated status | Done | Done | Both done | ✓ Synced
Breakdown AI selector | Done | Done | Both done | ✓ Synced
CSV/Document import | Done | Done | Both done | ✓ Synced
About page & User Guide | Done | Done | Both done | ✓ Synced