## Input
Row | Text
2 | Chatgpt
4 | Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file.
7 | 1) Optional but strongly recommended: allowlist only you + friends (Want setting off, but add a setting in admin to turn on and to set settings)
9 | If only you + 2 friends should access it, this is the biggest safety improvement for port-forwarded home hosting.
11 | Add this (edit the allowed IPs):
13 | ALLOWED_IPS = {"47.188.42.192", "FRIEND_IP_1", "FRIEND_IP_2"}
15 | @app.before_request
16 | def restrict_by_ip():
17 | ip = request.headers.get("X-Forwarded-For", request.remote_addr)
18 | ip = ip.split(",")[0].strip() # if multiple forwarded IPs
19 | if ip not in ALLOWED_IPS:
20 | return ("Forbidden", 403)
22 | 3.) When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them.
23 | Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs.
24 | 3.) In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them.
25 | Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look).
26 | Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns.
27 | If admin is logged in add "(Admin)" after User: **********
28 | If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****"
29 | "Key Accepted" should show on either project only if key is valid showing invalid if it isnt
31 | Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously.
32 | I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously.
34 | Most recent working zip version uploaded () use it as a base to these changes. Add:
36 | 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server.
38 | 2.) Remove old Logout button
40 | 3.)Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose.
42 | 4.) Setting to set to speak on both term and pronunciation
44 | 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings.
46 | 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings.
49 | 6.)
51 | a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups})
53 | b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups.
55 | c.) Add option to Change between Study subject flashcards via json files (manually or AI created)
57 | Added a Refresh / Reshuffle icon (⟳) that:
59 | only appears when Random order is ON
61 | does not toggle Random order
63 | only reshuffles when you click it
66 | Also in portrait orientation use a search icon like in landscape.
68 | Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon.
70 | Add a setting that when toggled on shows "Custom" Set Button on by default.
71 | In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default.
72 | Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.}
73 | In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action.
74 | Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page.
76 | 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings.
77 | 4.) In landscape orientation, as shown in screenshots, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text
79 | If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts (same card ID, different content)?
82 | x to clear search
83 | taping outside of search exits search but keeps results
84 | random setting for custom study
85 | remove custom trash function and icon dont need when having hide custom setting.
86 | button in custom settings that picks random blank # of unlearned cards in custom study.
87 | add randomize refresh icon when random is on
89 | Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page.
92 | Oh I see, the admin settings button has always been visible for sidscri and for Sidscri, but it does not open anything just a dead button. The "AI Access Settings" Section should be appearing, when admin actually opens its page.
96 | If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing.
98 | Saved breakdown text below "Select group..." dropdown does not change on changing cards
100 | Dont change color (white background, light grey text) of study/group dropdown list when changing from a group, cant see options.
102 | As admin to see who is actively/recently logged in and studying
104 | Notes to be added to cards, to view if selected. Option to share and collaberate with others.
108 | Next thing is to add png image and to change the color a little to match the company colors
110 | and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc.
112 | Run as service
114 | Turn this back into github to re-build the android app APK
116 | KenpoFlashCardsAndroidApp.zip with data, design, features from KenpoFlashcardsWeb.zip. So I may create a better version of the KenpoFlashcardsProject android app

## Android Pending
Row | Update Text | Status | Confidence | Evidence (files) | Web Status
7 | 1) Optional but strongly recommended: allowlist only you + friends (Want setting off, but add a setting in admin to turn on and to set settings) | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
11 | Add this (edit the allowed IPs): | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/README.md | Pending
13 | ALLOWED_IPS = {"47.188.42.192", "FRIEND_IP_1", "FRIEND_IP_2"} | Pending | Low |  | Pending
15 | @app.before_request | Pending | Low |  | Completed
16 | def restrict_by_ip(): | Pending | Low |  | Pending
17 | ip = request.headers.get("X-Forwarded-For", request.remote_addr) | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Completed
18 | ip = ip.split(",")[0].strip() # if multiple forwarded IPs | Pending | Low |  | Completed
19 | if ip not in ALLOWED_IPS: | Pending | Low |  | Pending
20 | return ("Forbidden", 403) | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
27 | If admin is logged in add "(Admin)" after User: ********** | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Pending
28 | If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Pending
34 | Most recent working zip version uploaded () use it as a base to these changes. Add: | Pending | Review | KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/JsonUtil.kt | Completed
38 | 2.) Remove old Logout button | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | Pending
49 | 6.) | Pending | Review |  | Pending
51 | a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Completed
55 | c.) Add option to Change between Study subject flashcards via json files (manually or AI created) | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/CsvImport.kt | Pending
57 | Added a Refresh / Reshuffle icon (⟳) that: | Pending | Low |  | Pending
63 | only reshuffles when you click it | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | Pending
68 | Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. | Pending | Review | KenpoFlashcardsProject-v2/README_FIRST.txt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
70 | Add a setting that when toggled on shows "Custom" Set Button on by default. | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Pending
79 | If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts (same card ID, different content)? | Pending | Review | KenpoFlashcardsProject-v2/README_FIRST.txt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | Pending
82 | x to clear search | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/CsvImport.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Pending
83 | taping outside of search exits search but keeps results | Pending | Low |  | Pending
85 | remove custom trash function and icon dont need when having hide custom setting. | Pending | Review | KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Pending
86 | button in custom settings that picks random blank # of unlearned cards in custom study. | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt | Pending
96 | If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt | Completed
98 | Saved breakdown text below "Select group..." dropdown does not change on changing cards | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Completed
100 | Dont change color (white background, light grey text) of study/group dropdown list when changing from a group, cant see options. | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/res/values/colors.xml; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json; KenpoFlashcardsProject-v2/README.md | Pending
102 | As admin to see who is actively/recently logged in and studying | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt | Pending
110 | and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/_wrapper_src/org/gradle/wrapper/GradleWrapperMain.java; KenpoFlashcardsProject-v2/README.md | Completed
112 | Run as service | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md | Pending
114 | Turn this back into github to re-build the android app APK | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
116 | KenpoFlashCardsAndroidApp.zip with data, design, features from KenpoFlashcardsWeb.zip. So I may create a better version of the KenpoFlashcardsProject android app | Pending | Review | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README_FIRST.txt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md | Pending

## Android Completed
Row | Update Text | Status | Confidence | Evidence (files) | Web Status
4 | Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. | Completed | Medium | KenpoFlashcardsProject-v2/CHANGELOG.md | Pending
9 | If only you + 2 friends should access it, this is the biggest safety improvement for port-forwarded home hosting. | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/_wrapper_src/org/gradle/wrapper/GradleWrapperMain.java; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt | Pending
22 | 3.) When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/Fixes v4.4.2 v22.txt | Completed
23 | Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/CHANGELOG.md | Pending
24 | 3.) In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/res/values/themes.xml; KenpoFlashcardsProject-v2/app/src/main/res/values/colors.xml | Completed
25 | Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Completed
26 | Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Completed
29 | "Key Accepted" should show on either project only if key is valid showing invalid if it isnt | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt | Pending
31 | Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Completed
32 | I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Completed
36 | 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed
40 | 3.)Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. | Completed | High | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Completed
42 | 4.) Setting to set to speak on both term and pronunciation | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt | Pending
44 | 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed
46 | 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed
53 | b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/GeminiHelper.kt | Completed
59 | only appears when Random order is ON | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/README_FIRST.txt | Completed
61 | does not toggle Random order | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed
66 | Also in portrait orientation use a search icon like in landscape. | Completed | High | KenpoFlashcardsProject-v2/Fixes v4.4.2 v22.txt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/Version-AndroidApp-v4.4.2 v22.txt; KenpoFlashcardsProject-v2/README.md | Pending
71 | In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Completed
72 | Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Completed
73 | In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
74 | Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. | Completed | High | KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Completed
76 | 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/README.md | Completed
77 | 4.) In landscape orientation, as shown in screenshots, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt | Completed
84 | random setting for custom study | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt | Completed
87 | add randomize refresh icon when random is on | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/README_FIRST.txt; KenpoFlashcardsProject-v2/README.md | Completed
89 | Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. | Completed | High | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed
92 | Oh I see, the admin settings button has always been visible for sidscri and for Sidscri, but it does not open anything just a dead button. The "AI Access Settings" Section should be appearing, when admin actually opens its page. | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt; KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json | Completed
104 | Notes to be added to cards, to view if selected. Option to share and collaberate with others. | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt; KenpoFlashcardsProject-v2/README.md; KenpoFlashcardsProject-v2/CHANGELOG.md; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt | Pending
108 | Next thing is to add png image and to change the color a little to match the company colors | Completed | Medium | KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt; KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/JsonUtil.kt; KenpoFlashcardsProject-v2/_wrapper_src/org/gradle/wrapper/GradleWrapperMain.java; KenpoFlashcardsProject-v2/CHANGELOG.md | Completed

## Web Pending
Row | Update Text | Status | Confidence | Evidence (files) | Android Status
4 | Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. | Pending | Review | KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
9 | If only you + 2 friends should access it, this is the biggest safety improvement for port-forwarded home hosting. | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/styles.css | Completed
11 | Add this (edit the allowed IPs): | Pending | Review | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
13 | ALLOWED_IPS = {"47.188.42.192", "FRIEND_IP_1", "FRIEND_IP_2"} | Pending | Review | KenpoFlashcardsWebServer/app.py | Pending
16 | def restrict_by_ip(): | Pending | Low |  | Pending
19 | if ip not in ALLOWED_IPS: | Pending | Review | KenpoFlashcardsWebServer/app.py | Pending
23 | Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. | Pending | Review | KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md | Completed
27 | If admin is logged in add "(Admin)" after User: ********** | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
28 | If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
29 | "Key Accepted" should show on either project only if key is valid showing invalid if it isnt | Pending | Review | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
38 | 2.) Remove old Logout button | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Pending
42 | 4.) Setting to set to speak on both term and pronunciation | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/app.py | Completed
49 | 6.) | Pending | Review |  | Pending
55 | c.) Add option to Change between Study subject flashcards via json files (manually or AI created) | Pending | Review | KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/about.html | Pending
57 | Added a Refresh / Reshuffle icon (⟳) that: | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Pending
63 | only reshuffles when you click it | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
66 | Also in portrait orientation use a search icon like in landscape. | Pending | Review | KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Completed
70 | Add a setting that when toggled on shows "Custom" Set Button on by default. | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/ai-access.html | Pending
79 | If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts (same card ID, different content)? | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/sitemap.xml; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Pending
82 | x to clear search | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/static/about.html | Pending
83 | taping outside of search exits search but keeps results | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js | Pending
85 | remove custom trash function and icon dont need when having hide custom setting. | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html | Pending
86 | button in custom settings that picks random blank # of unlearned cards in custom study. | Pending | Review | KenpoFlashcardsWebServer/app.py | Pending
100 | Dont change color (white background, light grey text) of study/group dropdown list when changing from a group, cant see options. | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/about.html | Pending
102 | As admin to see who is actively/recently logged in and studying | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
104 | Notes to be added to cards, to view if selected. Option to share and collaberate with others. | Pending | Review | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/static/admin.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Completed
112 | Run as service | Pending | Review | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md | Pending
116 | KenpoFlashCardsAndroidApp.zip with data, design, features from KenpoFlashcardsWeb.zip. So I may create a better version of the KenpoFlashcardsProject android app | Pending | Review | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/version.json; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Pending

## Web Completed
Row | Update Text | Status | Confidence | Evidence (files) | Android Status
7 | 1) Optional but strongly recommended: allowlist only you + friends (Want setting off, but add a setting in admin to turn on and to set settings) | Completed | Medium | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/index.html | Pending
15 | @app.before_request | Completed | High | KenpoFlashcardsWebServer/app.py | Pending
17 | ip = request.headers.get("X-Forwarded-For", request.remote_addr) | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/requirements.txt; KenpoFlashcardsWebServer/CHANGELOG.md | Pending
18 | ip = ip.split(",")[0].strip() # if multiple forwarded IPs | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js | Pending
20 | return ("Forbidden", 403) | Completed | High | KenpoFlashcardsWebServer/app.py | Pending
22 | 3.) When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
24 | 3.) In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | KenpoFlashcardsWebServer/static/about.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
25 | Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html | Completed
26 | Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/about.html | Completed
31 | Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/ai-access.html | Completed
32 | I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/index.html | Completed
34 | Most recent working zip version uploaded () use it as a base to these changes. Add: | Completed | Medium | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md | Pending
36 | 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/index.html | Completed
40 | 3.)Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/about.html | Completed
44 | 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/styles.css | Completed
46 | 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/styles.css | Completed
51 | a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/ai-access.html | Pending
53 | b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/README.md | Completed
59 | only appears when Random order is ON | Completed | Medium | KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
61 | does not toggle Random order | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/data/users/d58abe158e91/progress.json | Completed
68 | Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/user-guide.html | Pending
71 | In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. | Completed | High | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/d58abe158e91/progress.json; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | Completed
72 | Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} | Completed | High | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md | Completed
73 | In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/user-guide.html | Completed
74 | Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | Completed
76 | 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/data/users/d58abe158e91/progress.json | Completed
77 | 4.) In landscape orientation, as shown in screenshots, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text | Completed | Medium | KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/static/about.html | Completed
84 | random setting for custom study | Completed | Medium | KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/54af05fa7c22/progress.json | Completed
87 | add randomize refresh icon when random is on | Completed | High | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/data/users/d58abe158e91/progress.json | Completed
89 | Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/styles.css | Completed
92 | Oh I see, the admin settings button has always been visible for sidscri and for Sidscri, but it does not open anything just a dead button. The "AI Access Settings" Section should be appearing, when admin actually opens its page. | Completed | High | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/ai-access.html | Completed
96 | If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/styles.css; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/README.md | Pending
98 | Saved breakdown text below "Select group..." dropdown does not change on changing cards | Completed | High | KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/README.md | Pending
108 | Next thing is to add png image and to change the color a little to match the company colors | Completed | Medium | KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/static/index.html; KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/BRANDING_NOTE.md | Completed
110 | and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/user-guide.html; KenpoFlashcardsWebServer/static/styles.css | Pending
114 | Turn this back into github to re-build the android app APK | Completed | High | KenpoFlashcardsWebServer/app.py; KenpoFlashcardsWebServer/CHANGELOG.md; KenpoFlashcardsWebServer/static/app.js; KenpoFlashcardsWebServer/README.md; KenpoFlashcardsWebServer/static/user-guide.html | Pending

## Not in which project
Row | Update Text | Android | A Conf | Web | W Conf | Missing In | Evidence (A / W)
4 | Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. | Completed | Medium | Pending | Review | Web | A: KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/styles.css, KenpoFlashcardsWebServer/app.py
7 | 1) Optional but strongly recommended: allowlist only you + friends (Want setting off, but add a setting in admin to turn on and to set settings) | Pending | Review | Completed | Medium | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
9 | If only you + 2 friends should access it, this is the biggest safety improvement for port-forwarded home hosting. | Completed | Medium | Pending | Review | Web | A: KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/app.py
11 | Add this (edit the allowed IPs): | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/styles.css
13 | ALLOWED_IPS = {"47.188.42.192", "FRIEND_IP_1", "FRIEND_IP_2"} | Pending | Low | Pending | Review | Both | A: ¦ W: KenpoFlashcardsWebServer/app.py
15 | @app.before_request | Pending | Low | Completed | High | Android | A: ¦ W: KenpoFlashcardsWebServer/app.py
16 | def restrict_by_ip(): | Pending | Low | Pending | Low | Both | A: ¦ W:
17 | ip = request.headers.get("X-Forwarded-For", request.remote_addr) | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/about.html
18 | ip = ip.split(",")[0].strip() # if multiple forwarded IPs | Pending | Low | Completed | High | Android | A: ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
19 | if ip not in ALLOWED_IPS: | Pending | Low | Pending | Review | Both | A: ¦ W: KenpoFlashcardsWebServer/app.py
20 | return ("Forbidden", 403) | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt ¦ W: KenpoFlashcardsWebServer/app.py
22 | 3.) When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/about.html, KenpoFlashcardsWebServer/app.py
23 | Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. | Completed | High | Pending | Review | Web | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/about.html, KenpoFlashcardsWebServer/static/index.html
24 | 3.) In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/about.html, KenpoFlashcardsWebServer/app.py
25 | Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
26 | Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
27 | If admin is logged in add "(Admin)" after User: ********** | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
28 | If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
29 | "Key Accepted" should show on either project only if key is valid showing invalid if it isnt | Completed | High | Pending | Review | Web | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
31 | Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/README.md
32 | I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
34 | Most recent working zip version uploaded () use it as a base to these changes. Add: | Pending | Review | Completed | Medium | Android | A: KenpoFlashcardsProject-v2/README.md, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/CHANGELOG.md
36 | 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
38 | 2.) Remove old Logout button | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
40 | 3.)Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/CHANGELOG.md, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/user-guide.html
42 | 4.) Setting to set to speak on both term and pronunciation | Completed | High | Pending | Review | Web | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/index.html
44 | 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
46 | 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/index.html
49 | 6.) | Pending | Review | Pending | Review | Both | A: ¦ W:
51 | a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/user-guide.html
53 | b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
55 | c.) Add option to Change between Study subject flashcards via json files (manually or AI created) | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/user-guide.html, KenpoFlashcardsWebServer/static/about.html
57 | Added a Refresh / Reshuffle icon (⟳) that: | Pending | Low | Pending | Review | Both | A: ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/styles.css
59 | only appears when Random order is ON | Completed | Medium | Completed | Medium | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt ¦ W: KenpoFlashcardsWebServer/static/styles.css, KenpoFlashcardsWebServer/static/index.html
61 | does not toggle Random order | Completed | Medium | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/styles.css
63 | only reshuffles when you click it | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
66 | Also in portrait orientation use a search icon like in landscape. | Completed | High | Pending | Review | Web | A: KenpoFlashcardsProject-v2/Fixes v4.4.2 v22.txt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/styles.css, KenpoFlashcardsWebServer/static/index.html
68 | Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/README_FIRST.txt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
70 | Add a setting that when toggled on shows "Custom" Set Button on by default. | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
71 | In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
72 | Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
73 | In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Models.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/index.html
74 | Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/CHANGELOG.md, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
76 | 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
77 | 4.) In landscape orientation, as shown in screenshots, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text | Completed | High | Completed | Medium | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/styles.css, KenpoFlashcardsWebServer/static/index.html
79 | If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts (same card ID, different content)? | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/README_FIRST.txt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
82 | x to clear search | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/styles.css
83 | taping outside of search exits search but keeps results | Pending | Low | Pending | Review | Both | A: ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
84 | random setting for custom study | Completed | Medium | Completed | Medium | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt ¦ W: KenpoFlashcardsWebServer/static/styles.css, KenpoFlashcardsWebServer/static/index.html
85 | remove custom trash function and icon dont need when having hide custom setting. | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/README.md, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/README.md
86 | button in custom settings that picks random blank # of unlearned cards in custom study. | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Store.kt ¦ W: KenpoFlashcardsWebServer/app.py
87 | add randomize refresh icon when random is on | Completed | Medium | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
89 | Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. | Completed | High | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/README.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/index.html
92 | Oh I see, the admin settings button has always been visible for sidscri and for Sidscri, but it does not open anything just a dead button. The "AI Access Settings" Section should be appearing, when admin actually opens its page. | Completed | Medium | Completed | High | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/CHANGELOG.md ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/README.md
96 | If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/assets/kenpo_words.json ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
98 | Saved breakdown text below "Select group..." dropdown does not change on changing cards | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/ChatGptHelper.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/app.js
100 | Dont change color (white background, light grey text) of study/group dropdown list when changing from a group, cant see options. | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/res/values/colors.xml, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/CHANGELOG.md
102 | As admin to see who is actively/recently logged in and studying | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/app.py
104 | Notes to be added to cards, to view if selected. Option to share and collaberate with others. | Completed | Medium | Pending | Review | Web | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/index.html, KenpoFlashcardsWebServer/static/ai-access.html
108 | Next thing is to add png image and to change the color a little to match the company colors | Completed | Medium | Completed | Medium | None | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/JsonUtil.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/static/index.html
110 | and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/Repository.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/static/app.js
112 | Run as service | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/StudySettings.kt ¦ W: KenpoFlashcardsWebServer/static/app.js, KenpoFlashcardsWebServer/README.md
114 | Turn this back into github to re-build the android app APK | Pending | Review | Completed | High | Android | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/TtsHelper.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/CHANGELOG.md
116 | KenpoFlashCardsAndroidApp.zip with data, design, features from KenpoFlashcardsWeb.zip. So I may create a better version of the KenpoFlashcardsProject android app | Pending | Review | Pending | Review | Both | A: KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/WebAppSync.kt, KenpoFlashcardsProject-v2/app/src/main/java/com/example/kenpoflashcards/MainActivity.kt ¦ W: KenpoFlashcardsWebServer/app.py, KenpoFlashcardsWebServer/version.json