## List with Pending or Done
|  | App | Web
Changes I would like in project | Grouping of importance | Change in project Status | Change in project Status
Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. |  | Pending | Done
When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Done | Done
Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. |  | Done | Done
In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. |  | Done | Done
Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). |  | Done | Done
Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. |  | Done | Done
If admin is logged in add "(Admin)" after "Logged In:********" and "User:*****" |  | Pending | Pending
"Key Accepted" should show on either project only if key is valid showing invalid if it isnt |  | Done | Done
Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Done | Done
I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. |  | Done | Done
Most recent working zip version uploaded () use it as a base to these changes. Add: |  | Done | Done
1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. |  | Done | Done
2.) Remove old Logout button |  | Pending | Pending
Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. |  | Done | Done
Setting to set to speak on both term and pronunciation |  | Pending | Pending
5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Done | Done
6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. |  | Done | Done
a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) |  | Done | Done
b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. |  | Done | Done
c.) Add option to Change between Study subject flashcards via json files (manually or AI created) |  | Done | Done
Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it |  | Done | Done
Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. |  | Done | Done
In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. |  | Done | Done
Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} |  | Done | Done
In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. |  | Done | Done
Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. |  | Done | Done
Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. |  | Done | Done
In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. |  | Done | Done
1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) |  | Done | Done
Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. |  | Done | Done
4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text |  | Done | Done
In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. |  | Done | Done
If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. |  | Done | Done
Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. |  | Done | Done
If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. |  | Done | Done
Saved breakdown text below "Select group..." dropdown does not change on changing cards |  | Done | Done
As admin>Stats: to see who is actively/recently logged in and studying |  | Pending | Pending
Notes to be added to cards, to view if selected. Option to share and collaberate with others. |  | Done | Done
Next thing is to add png image and to change the color a little to match the company colors |  | Pending | Pending
Run as service |  | Pending | Pending
and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app. |  | Done | Done

## Android app version of change
Changes I would like in project | Grouping of importance | Change in project Status | Pending or Done

## Web Server version of change
Changes I would like in project | Grouping of importance | Change in project Status | Pending or Done

## Fix-Feature Implemented
Date | Project | Version | Build | Implemented items (Done)
2026-01-15 | Android App | 4.5.0 | 23 | • When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. • In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). • Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. • "Key Accepted" should show on either project only if key is valid showing invalid if it isnt • Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • Most recent working zip version uploaded () use it as a base to these changes. Add: • 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. • Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. • 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) • b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. • c.) Add option to Change between Study subject flashcards via json files (manually or AI created) • Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it • Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. • In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. • Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} • In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. • Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. • Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. • In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. • 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) • Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. • 4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text • In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. • If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. • Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. • If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. • Saved breakdown text below "Select group..." dropdown does not change on changing cards • Notes to be added to cards, to view if selected. Option to share and collaberate with others. • and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app.
2026-01-15 | Web Server | 5.6.0 | 30 | • Add server log in admin settings, Tabbed by Server logs, error logs, user logs. Make downloadable and resettable in gui by starting a new log file. • When you click on User: ********* it opens a dropdown sub window where the current version will be shown, "Admin" Button to open Admin page. in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me. and a description, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Add "Web App Sync" section into newly a created "Sync Progress" page within "User: *********" So users may see Sync status history progress and breakdown syncs. • In More add Current Version of App. Create an about page in more, in the root of the "About" page have "Created by Sidney Shelton" With email Sidscri@yahoo.com for questions and feature requests to be filled in and emailed to me Sidscri@yahoo.com. and a description of the app, major features of the project. Would like a download/printable "User Guide" all the features and how to use them. • Move non admin users Login Fields and section as it is now into its own "Login" page, put "Login" button inplace of current "admin settings" button {only show Admin Settings for admins (Sidscri, for now)}, Move "Web App Sync" section without login (With Push and Pull Button only,) add "Login Status:" text and "Sync Breakdowns" section with button from "Admin Settings" into newly created "Sync Progress" page within "More" below newly created "Login" button (Keeping Current login section look). • Keep "ChatGPT API" and newly added "Gemini API" section in admin page. Have "Web App Sync" auto Pull progress and Breakdowns after initial login. Add a setting to Pull automatically everytime you login or not. and setting to auto push app progress and breakdowns to server when changed; sync pending changes while offline upon online status if possible), if not, inform via text aside "Sync Progress" button. Make sure Sync on first time logging in on device is always on (no setting needed). but the setting only applys to future logins on previously logged into app. Auto Sync off by default, unless there is a way to keep track of what card status is new via time stamp and which is outdated and can be over ridden to andor from either project, so it makes the auto sync function more helpful and would be a benefit of keeping it one. Should have setting and function the same for breakdowns. • "Key Accepted" should show on either project only if key is valid showing invalid if it isnt • Like ChatGPT also have an option to add gemini API to android apps admin settings, on save it pushes both encrypted api key(s) to server's helper json or a special encrypted file (like encrypted passwords) So it can be commited and push safely to github, so on future app installs or user logins the encrypted key will be automatically pulled, like we have for cards data, progress, and breakdown data, to its spot in admin (with option to type in a replacement key that would go back throught the same process on the server side) and to its admins API spot. Inside "AI Access Settings" Section should have ChatGPT API Field and Gemini API field, where if already encrypted in server file will already be showing as "Key Accepted" if key is valid, "Key Invalid" if not.. select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • I want users in "More" >"Sync Progress" (below "Login" button) > "Sync Breakdowns" section Below "Web App Sync" (with "Push" and "Pull" buttons, and status text) to be able to select Breakdown AI service from a drop down or up box in "Sync Breakdowns" section and above "Sync Breakdowns" button to have a "Choose Breakdown AI" button to select ; "Auto Select" (Best result wins, only if both API keys are present), or choose from "ChatGPT", or "Gemini" showing only If their independant key has been added by admin previously. • Most recent working zip version uploaded () use it as a base to these changes. Add: • 1.) When I click on "User: *********". Add "Logout" Button, "Admin" button (Only Accessable by admin (Sidscri) that opens an admin page. Inside Admin page will be (in no specific order) stats, of who is currently logged in, and recent activity, List of all users registered, ability to give admin to any user, reset any users password to "12345678" then require the next time that user tries to login it will prompts a password change, logging, error logs both to be saved in data folder on server. • Have option to change "Unlearned" "Unsure" "Learned">"Study" individually from Flash Card method to Multiple choose. • 5.) Add a "Custom" deck to the right of "ALL". With a setting to turn on "Add Custom Study Deck" on by default. Add Mark Cards icon (star) button in "All" cards to add to "Custom" deck. In the "Custom" page add a remove from "Custom" page icon (Trash can). I Want to be able to further add them to Custom only subdecks ("Unsure" & "Learned" views) within the "Custom" page only. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes in Main Decks also" (Main decks="Unlearned", "Unsure", "Learned", "All"), off by default. Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • 6.) Inside the admin page will be a setting off by default when turn on it will add another Deck to the right of "All" and "Custom" (if turn on). This Deck is for static cards to be selected by admins (sidscri) via check box in drop down with <admin generated button text>, and <admin generated page title> to be added within the page and have a save button for all users to study a specific set of cards. All formatting will be the same as other study decks, with its own <admin generated page title> page only subdecks ("Unsure" & "Learned" views). Add a setting only in this <admin generated title> page when turned on will say "Reflect <admin generated title> status changes in Main Decks also", off by default (defaults to off after admin turns off and on or presses Clear <admin generated title> defaults button). Remove any non <admin generated title> deck related settings just within the <admin generated title> page setting, i.e. keeping <admin generated title> only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. • a.) Add to existing flashcard json via Manually adding Terms and Definitions; with optional AI generated Definitions, AI generated pron., AI generated groups {can limit to max # of groups}) • b.) Create new jsons by adding existing external study list via: > Uploaded pictures > Uploaded documents (pdf,word,text,csv,excel/google sheets) > AI Search for specific subjects using keywords (set max card quanity and an option to select from found terms from search to add to list in json file). All lists in json files will be created by AI scanning files/pictures with AI generated terms, AI generated Definitions, AI generated pron., AI generated groups. • c.) Add option to Change between Study subject flashcards via json files (manually or AI created) • Added a Refresh / Reshuffle icon (⟳) that: only appears when Random order is ON, only reshuffles when you click it • Remove the top bar where the page title is i.e "Unsure" page title in orientation is. Unnecessary waste of screen since that Page title is already present to the left of the search icon. • In "Custom" page only, "To Study : ##" will be replaced by Custom: ##. "Custom: ##", "Unsure: ##", "Learned: ##" should reflect status of "Custom" set only. Meaning if I press "got it" or "unsure" or "Relearn" button, cards move to subpages within the "Custom" set page only without changing anything on the main status. Clicking on Custom: ##, Unsure: ##, Learned: ##, will go to that subpage with their study cards status, i.e. from "Custom" to "Learned" status, and back to the "Custom" list without reflecting the status of the main status. Add a setting only in "Custom" page when turned on will say "Reflect Custom status changes to Main Decks also", off by default. • Remove any non "Custom" deck related settings just within the "Custom" page setting, i.e. keeping Custom only "Random Order", "Reverse the cards", "Show group label", "Remove breakdown & literal meaning", "Order of cards", "Show definitions", "Show Unlearned & Unsure buttons" No need to have general settings like AI, speak, any future general app wide settings. In the Learned page dont show the second Learned: ## text. In the Custom page have all four :## all in one row, will need to shrink the text a little to make them fit without looking cramped.} • In Custom put "Unsure" button back across from "Got it" where the "Remove" button currently is. Turn the current remove All icon on top right to only remove current card, confirm action. • Add a button in custom only settings that opens a page to set a number of random # of unlearned cards from all into custom study. Icon will be a dice. • Replace the search field with a search icon (Magnifying Glass in "Learned">"List". Like its done in "Learned">"Study" and the others). Make "Custom" and "Learned>Study" page look like "To Study" and "Unsure" page. • In search press x to clear search, taping outside of search exits search but keeps results, in settings add random setting for custom study. • 1.) in the "all" page the "Active" and "Unsure" buttons are smooshed so the text aren't visible in either orientation. 2.) • Also in the "all" page Rename "Active" action to "Relearn", and rename status text from "Active" to "To Learn" 3.) Remove "Reset all progress" in setting and replace with "Reset to Default Settings", use screenshot uploaded as default settings. • 4.) In landscape orientation, "Learned" and "All" pages are not good, remove bottom :Learned:***" status text • In landscape, the card and button on right are not filling the page, to much space at bottom. See if you can remove white bar over phone clock icons and over phone action "buttons". Or make same color as backround allowing phone time, notification bar to be see as well as action buttons on right. • If you want bidirectional sync (push local breakdowns to server too), I can add that. What behavior do you want for conflicts most recent change card status wins. Most recent breakdown wins. Need to add time stamp status on cards in helper json to determine which one is newest. Meaning if half of the unsynced status was done on the web, while the other half was done on app it will be able to merge changes between the devices. • Option to replace term side of card with "press speak to listen to Term" so we can only hear the word then flip for answer to be spoken. Setting to universally speak the definition on flip. I want a speak button to speak definitions when showing definition side. Add "**** End of Deck**** " under that text on card put "Tap to Return to Top" button. Replacing the return to top button at the bottom of page. • If breakdawn data is present I want a small icon on all cards with data to show it present. Maybe under the Status: or definition on definition page. With a quick view if pressed with auto closing. • Saved breakdown text below "Select group..." dropdown does not change on changing cards • Notes to be added to cards, to view if selected. Option to share and collaberate with others. • and to have an icon for it to show with the other apps running in the background i.e. wifi, bluetooth, Windows security, etc. When using service app.